## Sheet1
		1ST WEEK	2ND WEEK	3RD WEEK	4TH WEEK	TOTAL
GDD		4 HOURS				4 HOURS
DEVELOPMENT	BATTLE UI DESIGN	1 HOUR				20 HOURS
	PHYSICAL BATTLEGROUND LIMITS		1 HOUR
	PLAYER CHARACTER ANIMATIONS		2 HOURS
	PLAYER CHARACTER CONTROLS		2 HOURS
	PHYSICAL CHARACTERS INTERACTIONS		4 HOURS
	ENEMY AI BEHAVIOUR			6 HOURS
	MAIN MENU DESIGN			1 HOUR
	INTRO SCENE DESIGN			1 HOUR
	STORY, ENDING AND CREDITS			1 HOUR
	BUILDING				1 HOUR
MARKETING					6 HOURS	6 HOURS
TESTING					5 HOURS	5 HOURS
TOTAL		5 HOURS	9 HOURS	9 HOURS	12 HOURS	35 HOURS