## Sheet1
		SEMANA 1	SEMANA 2	SEMANA 3	SEMANA 4	TOTAL
GDD		4 HOURS				4 HOURS
DEVELOPMENT	BATTLE UI DESIGN	1 HOUR				20 HOURS
	PHYSICAL BATTLEGROUND LIMITS		1 HOUR
	PLAYER CHARACTER ANIMATIONS		2 HOURS
	PLAYER CHARACTER CONTROLS		2 HOURS
	PHYSICAL CHARACTERS INTERACTIONS		4 HOURS
	ENEMY AI BEHAVIOUR			6 HOURS
	MAIN MENU DESIGN			1 HOUR
	INTRO SCENE DESIGN			1 HOUR
	STORY, ENDING AND CREDITS			1 HOUR
	BUILDING				1 HOUR
MARKETING					6 HOURS	6 HOURS
TOTAL		5 HOURS	10 HOURS	10 HOURS	5 HOURS	30 HOURS